## Priority Updated TP
Test Plan
# | Feature | Feature Details | Inter-Features Overlapping | Test Name | Reference | Test description | Type(Negative /positive) | Priority | Status (Pass/Fail/ Cancel/Merge) | Progress
1 | Reset | * CTRL FSM should go to IDLE state. -Reset should be maintained for 200µs -CKE should be pulled low before reset is deasserted (min 10 ns). - CKE must be continuously registered “High” until the initialization sequence is finished | ….. | ddr4_mc_test_1_rst | JEDEC_79-4 sec3.3 p. 17 | 1. Deassert reset_n initially. 2. Assert reset after 200ns. 3. De-assert reset after 200µs. 4. assert CKE is active after tCKE - tIS. 5. Wait for initialization sequence 6.Apply Reset in the middle of R/W. | positive | 1 | 1.PASS 2.PASS 3. FAILED 4. FAILED 5. PASS 6. Pending
2 | Power-up and Initialization | * CTRL FSM should go to INITIALIZATION state. * CKE should be pulled high 500µs after reset. * A Deselect command must be issued. * CKE must kept pulled high during initialization. * MRS registers should be loaded with application settings. * FSM should go back to ACTIVATE state when done. | Reset | ddr4_mc_test_2_pwr | JEDEC_79-4 sec 3.3.1 p. 17-18 | 1. assert tXPR is satisfied. 2. Assert CKE hold time 3. assert cs_n = 0, act_n = 1, ras_n_a16= 0, cas_n_a15 = 0, we_n_a15 = 0, BG0 =1, BA1:BA0=11 for MR3 4. assert BG0 =1, BA1:BA0=10 for MR6 5. assert BG0 =1, BA1:BA0=01 for MR5. 6. assert BG0 =1, BA1:BA0=00 for MR4; 7. assert BG0 =0, BA1:BA0=10 for MR2; 8. assert BG0 =0, BA1:BA0=01 for MRS1 9. assert BG0 =0 BA1:BA0 = 00 for MR0 10. Assert ZQCL is issued . 11. Generate BL, CWL, CL and tCCD 12.Assert tMOD between successive MRS 13. Assert tMRD between MRS0 and ZQCL | positive | 1 | ALL PASSED
3 | Activate | Activation of a row in a patricular bank Randomized testing | Power-up and initialization | ddr4_mc_test_3_act | JEDEC_79-4 sec4.22 p.90 | 1. generate r/w request. 2. assert tZQ 3. assert cs_n = 0 4. assert act_n = 0 5. assert tRRD. 6. generate address with random values 7. generate data with random values 8. monitor next_state register 9. get coverage | positive | 1 | 1. PASS 2. PASS 3. PASS 4. PASS 5. PASS
4 | Activate | Activation of a row in a patricular bank Directed testing | Power-up and initialization | ddr4_mc_test_4_act | JEDEC_79-4 sec4.22 p.90 | 1. generate the same address twice(direct assignment) 2. monitor next_state register 3. generate address of same bank different row 4. assert tRP 5. monitor next_state register 6. Repeat for all 16 banks | 1. positive 2. negative | 1 | 1. PASS 2. PASS 3. PASS 4. PASS 5. PASS 6. Pending
| Write Operation | *Perform a memory write *Depending on the burst length, data should valid on the DQ bus *Data should be written to memory | Activate | ddr4_mc_test_6_wr | JEDEC_79-4 sec4.25 p.107 | 1. issue write request 2. generate random address 3. assert tRCD 4. genrate another write 5. assert tCCD 5. assert CWL 6. monitor next_state register. 7. monitor memory contents 8. two consecutive writes to same row 9. assert tCCD 10. write to different row, same bank 11. assert tWTP 10. repeat for all 16 banks |  |  | 1. PASS 2.Pending 3. PASS 4. PASS 5. PASS 6. PASS 7. Pending 8. PASS 9. PASS 10. PASS 11. PASS
| Read Operation | *Perform a memory read. *The FSM should go to READ state. *Depending on the burst length, data should valid on the DQ bus | Activate | ddr4_mc_test_5_rd | JEDEC_79-4 sec4.24 p.84 | 1. issue read request 2. generate random address 3. assert tRCD 4. issue another read 5. assert tCCD 6. issue a write after read 7. assert tCCD 8. two consecutive reads to same row 9. assert tCCD 10. read from different row, same bank 11. assert tRTP 5. repeat for all 16 banks | positive | 1 | 1. PASS 2. Pending 3. PASS 4. PASS 5. PASS 6. PASS 7. PASS 8. PASS 9. PASS 10. PASS 11. PASS
| Refresh | The DDR4 should perform a Refresh cycles at an average periodic interval of tREFI *Address bits should be set to X *FSM should go to IDLE state |  | ddr4_mc_test_5_rfrsh | JEDEC_79-4 sec4.26 p. 123 | 1. monitor tREFI. 2. when tREFI is satisfied, monitor next state register 3. Assert tRFC | 1.positive 2.negative | 1 | 1. PASS 2. PASS 3. Cancel
| Update Operation | The DDR4 should issue an MRS command to MR0 to update to the burst length from 4 to 8 or vise versa *The controller should be in the IDLE state *The controller should not accept any other commands while updating |  | ddr4_mc_test_7_Update |  | 1.issue a reset *issue an update command *monitor next_state register *load MR0 *repeat read or write and monitor data out 2.issue activate while in update | 1.positive 2.negative | 1
| Functional Coverage tests | Grouping coverpoints to achieve functional coverage |  | ddr4_mc_test_8_cover |  | 1. All 4 bank groups should be addressed. 2. All 4 banks/bank group should be addresed 3. Set of possible addresses in memory space 4. All four operations should be tested:ignoring NOP 5. All possible valid commands should be invoked 6. All possible values of user programmed delays should be tested |  | 1
| Code Coverage | FSM Coverage |  | ddr4_mc_test_9_cover |  | Controller FSM coverage